## Sheet1
Risk ID | Risk Description | Likelihood (High/Med/Low) | Impact (High/Med/Low) | Risk Score (L x I) | Response Strategy | Owner | Status
R1 | Some laptops may not meet Windows 11 hardware requirements | High | High | High | Pre-check all devices, replace non-compliant units early | IT Operations Lead | Open
R2 | Applications may not be compatible with Windows 11 | Medium | High | High | Test all critical applications in pilot phase and resolve issues | BA Team / Application Owners | Open
R3 | End users may resist change or fail to adopt new OS | Medium | Medium | Medium | Run change management and comms campaigns to ease adoption | Change Management Lead | Monitoring
R4 | Delays in procurement of replacement hardware | Low | High | Medium | Engage procurement early and validate lead times | Procurement Manager | Watching
R5 | Security configuration may not align with corporate policy | Medium | High | High | Conduct security review and adjust policies before rollout | Security Lead | Open