## Sheet1
Project Activity | Project Sponsor | Lead Project Manager | IT Operations Lead | Security Lead | Business Unit Rep | End Users (Group)
Define Migration Scope | A | R | C | C | C
Hardware Readiness Checks |  | A | R
Application Compatibility Testing |  | A | C | C |  | C
Pilot Rollout Execution |  | A | R |  | C | I
Full Deployment Scheduling | C | A | R |  | R | I
User Training and Support |  | C | C |  | A | R
Security Review and Approval | C | C |  | R
Project Reporting and Updates | A | R |  | C | I
Responsible
Accountable
Consulted
Informed